## workers
Ahren Brendan | AB
Burjan Peter | BP
Cracium Sorin | CS
Dowling Garrett | DG
Hennessy Stephen | HS
Klimas Robert | KR
Murphy Martin | MM
Nagler Martin | NM
Lutz Omar | LO
Hoti Dritten | HD
Daly Brian | DB
Mecerod Michal | ME
Rabijac Zlatko | RZ
Fischer Peter | FP
Bretz Anatoli | BA
Scalera Joe | SJ
Bracher Raimond | BR
Hoff Jörg | HJ
Träger Marcel | TM
Ihlhoff Hansjörg | I H
Weinkoop Christopher | WC
Popodi Patrick | PO
Mitterrutzner Franz | MF
Morelli Mario | MO
Donelan Patrick | DP
Zsolt Tercsi | ZT
Klose Thomas | KT
Cerrelli Vincenzo | CV
Mitkov Alexander | MA
Egli Cyrill | EC
Petrezsely Henrik | PH
Windlin Nikolaus | WN
Torro Belda Javier | TB
Gentian Dai | GD
Teuber Chris | TC
Rodriguez Rafael | RR
Henryk Miotke | HM
Lemka Waldemar | LW
Lemka Marcin | LM
Radoslav Pavlovic | RP
Ricardo Peres Da Silva | RS

## activities
B | Substructure façade
C | Frame installation
D | Glazing modules installation
E | Sealing & Insulation

## Processes
AB01 | AB01

## activityProcessRelation
B | AB01
C | AB01
D | AB01
E | AB01

## LBS-level1
levelID | description
X1 | Level 0
X2 | Level 1
X3 | Level 2

## LBS-level2
id | orientation
EAB | Zone E/AB
EBC | Zone E/BC
ECD | Zone E/CD
SA1B1 | Zone S/A'B'
SB1C1 | Zone S/B'C'
SC1D1 | Zone S/C'D'
WAB | Zone W/AB
WBC | Zone W/BC
WCD | Zone W/CD

## columns (hidden)
acronym | column
AK/T | AK/T
T | T
AT | Arbeitstage
E | Einheit
M | Menge
M/AT | Menge pro Arbeitstag
M/h | M/h
M/w | M/w
A | Ausrichtung
NA | No of Ausrichtung
F | Stockwerk
NF | No of Stockwerk
MT | Manntage
h | Arbeitsumfang

## TempQuantities
[8 empty] | h/AT | 8 |  |  | LAWS | 4
[8 empty] | h/w | 40
Gewerk |  |  | AB01 - AB01
| Arbeitsgang |  | AK/T | T | AT | E | M | M/AT | M/h | M/w | A | NA | F | NF | MT | h
AB01 | Substructure façade | B | 2 | 1 | 7 | pcs | 135 | 19.2857 | 2.4107 | 96.4286 | EAB,EBC,ECD,SA1B1,SB1C1,SC1D1,WAB,WBC,WCD | 9 | 01-03 | 3 | 14 | 112
AB01 | Frame installation | C | 2 | 1 | 13 | pcs | 261 | 20.0769 | 2.5096 | 100.3846 | EAB,EBC,ECD,SA1B1,SB1C1,SC1D1,WAB,WBC,WCD | 9 | 01-03 | 3 | 26 | 208
AB01 | Glazing modules installation | D | 2 | 1 | 13 | pcs | 261 | 20.0769 | 2.5096 | 100.3846 | EAB,EBC,ECD,SA1B1,SB1C1,SC1D1,WAB,WBC,WCD | 9 | 01-03 | 3 | 26 | 208
AB01 | Sealing & Insulation | E | 2 | 1 | 16 | pcs | 261 | 16.3125 | 2.0391 | 81.5625 | EAB,EBC,ECD,SA1B1,SB1C1,SC1D1,WAB,WBC,WCD | 9 | 01-03 | 3 | 32 | 256
784
AB01 | 784
Grand Total | 784

## TemplocationMatrix
|  |  | X1 - Level 0 | X1 - Level 0 | X1 - Level 0 | X1 - Level 0 | X1 - Level 0 | X1 - Level 0 | X1 - Level 0 | X1 - Level 0 | X1 - Level 0 | X2 - Level 1 | X2 - Level 1 | X2 - Level 1 | X2 - Level 1 | X2 - Level 1 | X2 - Level 1 | X2 - Level 1 | X2 - Level 1 | X2 - Level 1 | X3 - Level 2 | X3 - Level 2 | X3 - Level 2 | X3 - Level 2 | X3 - Level 2 | X3 - Level 2 | X3 - Level 2 | X3 - Level 2 | X3 - Level 2 | Floors
Gewerk | Activities |  | EAB | EBC | ECD | SA1B1 | SB1C1 | SC1D1 | WAB | WBC | WCD | EAB | EBC | ECD | SA1B1 | SB1C1 | SC1D1 | WAB | WBC | WCD | EAB | EBC | ECD | SA1B1 | SB1C1 | SC1D1 | WAB | WBC | WCD | Orientations
|  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
AB01 | B | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
AB01 | C | 12 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
AB01 | D | 12 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
AB01 | E | 12 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12

## InputQuantities
[8 empty] | h/D | 8 |  |  | LAWS | 4
[8 empty] | h/w | 40
Process |  |  | AB01 - AB01
| Activity |  | AK/T | T | AT | E | M | M/AT | M/h | M/w | A | NA | F | NF | MT | h
AB01 | Substructure façade | B | 2 | 1 | 7 | pcs | 135 | 19.2857 | 2.4107 | 96.4286 | EAB,EBC,ECD,SA1B1,SB1C1,SC1D1,WAB,WBC,WCD | 9 | 01-03 | 3 | 14 | 112
AB01 | Frame installation | C | 2 | 1 | 13 | pcs | 261 | 20.0769 | 2.5096 | 100.3846 | EAB,EBC,ECD,SA1B1,SB1C1,SC1D1,WAB,WBC,WCD | 9 | 01-03 | 3 | 26 | 208
AB01 | Glazing modules installation | D | 2 | 1 | 13 | pcs | 261 | 20.0769 | 2.5096 | 100.3846 | EAB,EBC,ECD,SA1B1,SB1C1,SC1D1,WAB,WBC,WCD | 9 | 01-03 | 3 | 26 | 208
AB01 | Sealing & Insulation | E | 2 | 1 | 16 | pcs | 261 | 16.3125 | 2.0391 | 81.5625 | EAB,EBC,ECD,SA1B1,SB1C1,SC1D1,WAB,WBC,WCD | 9 | 01-03 | 3 | 32 | 256
784
AB01 | 784
Grand Total | 784

## locationMatrix
|  | X1 - Level 0 | X1 - Level 0 | X1 - Level 0 | X1 - Level 0 | X1 - Level 0 | X1 - Level 0 | X1 - Level 0 | X1 - Level 0 | X1 - Level 0 | X2 - Level 1 | X2 - Level 1 | X2 - Level 1 | X2 - Level 1 | X2 - Level 1 | X2 - Level 1 | X2 - Level 1 | X2 - Level 1 | X2 - Level 1 | X3 - Level 2 | X3 - Level 2 | X3 - Level 2 | X3 - Level 2 | X3 - Level 2 | X3 - Level 2 | X3 - Level 2 | X3 - Level 2 | X3 - Level 2 | Floors
Process | Activities | EAB | EBC | ECD | SA1B1 | SB1C1 | SC1D1 | WAB | WBC | WCD | EAB | EBC | ECD | SA1B1 | SB1C1 | SC1D1 | WAB | WBC | WCD | EAB | EBC | ECD | SA1B1 | SB1C1 | SC1D1 | WAB | WBC | WCD | Orientations
AB01 | B | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
AB01 | C | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
AB01 | D | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
AB01 | E | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12

## Week1
[65 empty] | Codes | Description |  |  | Field | Value |  | Presence List
[65 empty] | Yes | Yes |  |  | h/D | 9 |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 41 | WR
[65 empty] | No | No |  |  | d | 5 |  | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd.
[65 empty] | J-ML | Management and logistics |  |  | h/W | 45 |  | AB | BP | CS | DG | HS | KR | MM | NM | LO | HD | DB | ME | RZ | FP | BA | SJ | BR | HJ | TM | I H | WC | PO | MF | MO | DP | ZT | KT | CV | MA | EC | PH | WN | TB | GD | TC | RR | HM | LW | LM | RP | RS
[65 empty] | J-S | Special work | [5 empty] | 41.1724 | 41.1724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82.3448 | Scheduled
[65 empty] | J-A | Additional work |  |  |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 1845 | Total
[65 empty] | fd. | Full day
[65 empty] | hd. | Half day
Week1 Scheduling
[5 empty] | X1 - Level 0 | [17 empty] | X2 - Level 1 | [17 empty] | X3 - Level 2 | [10 empty] | Offer | [14 empty] | MA / Crew
|  |  | Performance |  | EAB |  | EBC |  | ECD |  | SA1B1 |  | SB1C1 |  | SC1D1 |  | WAB |  | WBC |  | WCD |  | EAB |  | EBC |  | ECD |  | SA1B1 |  | SB1C1 |  | SC1D1 |  | WAB |  | WBC |  | WCD |  | EAB |  | EBC |  | ECD |  | SA1B1 |  | SB1C1 |  | SC1D1 |  | WAB |  | WBC |  | WCD |  |  |  |  | Crew 1 |  | Crew 2 | 1 | 2 | 1 | 2 |  |  |  | AB | BP | CS | DG | HS | KR | MM | NM | LO | HD | DB | ME | RZ | FP | BA | SJ | BR | HJ | TM | I H | WC | PO | MF | MO | DP | ZT | KT | CV | MA | EC | PH | WN | TB | GD | TC | RR | HM | LW | LM | RP | RS |  |  | Working hours crew 1 | [5 empty] | Working hours crew 2
Process | Activity |  | QTY/W | WR | [54 empty] | TUS | WR | h |  |  |  | Fe | Fe | MA | MA |  |  |  | AB | BP | CS | DG | HS | KR | MM | NM | LO | HD | DB | ME | RZ | FP | BA | SJ | BR | HJ | TM | I H | WC | PO | MF | MO | DP | ZT | KT | CV | MA | EC | PH | WN | TB | GD | TC | RR | HM | LW | LM | RP | RS |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | SNo. | Jolly | Name | Cod | h
AB01 | Substructure façade | B | 96.4286 | 2 | 5 | -5 | 5 | -5 | 5 | -5 | 5 | -5 | 5 | -5 | 5 | -5 | 5 | -5 | 5 | -5 | 5 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 45 | 2 | 42 | AB | BP |  | 45 | 0 | 2 | 0 |  |  |  | 21 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1: 21; 2: 21 | 1 | Yes |  |  | 0
AB01 | Frame installation | C | 100.3846 | 2 | 5 | -5 | 5 | -5 | 5 | -5 | 5 | -5 | 5 | -5 | 5 | -5 | 5 | -5 | 5 | -5 | 5 | -5 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 45 | 2 | 40.3448 | AB | BP |  | 45 | 0 | 2 | 0 |  |  |  | 20.1724 | 20.1724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1: 20.1724; 2: 20.1724 | 2 | Yes |  |  | 0
AB01 | Glazing modules installation | D | 100.3846 | 2 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 3 | Yes |  |  | 0
AB01 | Sealing & Insulation | E | 81.5625 | 2 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 4 | Yes |  |  | 0
[128 empty] | 5 | Yes |  |  | 0
[128 empty] | 6 | Yes |  |  | 0
[128 empty] | 7 | Yes |  |  | 0
[128 empty] | 8 | Yes |  |  | 0
[128 empty] | 9 | Yes |  |  | 0
[128 empty] | 10 | Yes |  |  | 0
[128 empty] | 11 | Yes |  |  | 0
[128 empty] | 12 | Yes |  |  | 0
[128 empty] | 13 | Yes |  |  | 0
[128 empty] | 14 | Yes |  |  | 0
[128 empty] | 15 | Yes |  |  | 0
[128 empty] | 16 | Yes |  |  | 0
[128 empty] | 17 | Yes |  |  | 0
[128 empty] | 18 | Yes |  |  | 0
[128 empty] | 19 | Yes |  |  | 0
[128 empty] | 20 | Yes |  |  | 0
[128 empty] | 21 | Yes |  |  | 0
[128 empty] | 22 | Yes |  |  | 0
[128 empty] | 23 | Yes |  |  | 0
[128 empty] | 24 | Yes |  |  | 0
[128 empty] | 25 | Yes |  |  | 0
[128 empty] | 26 | Yes |  |  | 0
[128 empty] | 27 | Yes |  |  | 0
[128 empty] | 28 | Yes |  |  | 0
[128 empty] | 29 | Yes |  |  | 0
[128 empty] | 30 | Yes |  |  | 0
[128 empty] | 31 | Yes |  |  | 0
[128 empty] | 32 | Yes |  |  | 0
[128 empty] | 33 | Yes |  |  | 0
[128 empty] | 34 | Yes |  |  | 0
[128 empty] | 35 | Yes |  |  | 0
[128 empty] | 36 | Yes |  |  | 0
[128 empty] | 37 | Yes |  |  | 0
[128 empty] | 38 | Yes |  |  | 0
[128 empty] | 39 | Yes |  |  | 0
[128 empty] | 40 | Yes |  |  | 0
[128 empty] | 41 | Yes |  |  | 0

## Week2
[64 empty] | Codes | Description |  |  | Field | Value |  | Presence List
[64 empty] | Yes | Yes |  |  | h/D | 9 |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 41 | WR
[64 empty] | No | No |  |  | d | 5 |  | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd.
[64 empty] | J-ML | Management and logistics |  |  | h/W | 45 |  | AB | BP | CS | DG | HS | KR | MM | NM | LO | HD | DB | ME | RZ | FP | BA | SJ | BR | HJ | TM | I H | WC | PO | MF | MO | DP | ZT | KT | CV | MA | EC | PH | WN | TB | GD | TC | RR | HM | LW | LM | RP | RS
[64 empty] | J-S | Special work | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Scheduled
[64 empty] | J-A | Additional work |  |  |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 1845 | Total
[64 empty] | fd. | Full day
[64 empty] | hd. | Half day
Week2 Scheduling
[5 empty] | X1 - Level 0 | [17 empty] | X2 - Level 1 | [17 empty] | X3 - Level 2 | [10 empty] | Offer | [13 empty] | MA / Crew
|  |  | Performance |  | EAB |  | EBC |  | ECD |  | SA1B1 |  | SB1C1 |  | SC1D1 |  | WAB |  | WBC |  | WCD |  | EAB |  | EBC |  | ECD |  | SA1B1 |  | SB1C1 |  | SC1D1 |  | WAB |  | WBC |  | WCD |  | EAB |  | EBC |  | ECD |  | SA1B1 |  | SB1C1 |  | SC1D1 |  | WAB |  | WBC |  | WCD |  |  |  |  | Crew 1 | Crew 2 | 1 | 2 | 1 | 2 |  |  |  | AB | BP | CS | DG | HS | KR | MM | NM | LO | HD | DB | ME | RZ | FP | BA | SJ | BR | HJ | TM | I H | WC | PO | MF | MO | DP | ZT | KT | CV | MA | EC | PH | WN | TB | GD | TC | RR | HM | LW | LM | RP | RS |  |  | Working hours crew 1 | [5 empty] | Working hours crew 2
Process | Activity |  | QTY/W | WR | [54 empty] | TUS | WR | h |  |  | Fe | Fe | MA | MA |  |  |  | AB | BP | CS | DG | HS | KR | MM | NM | LO | HD | DB | ME | RZ | FP | BA | SJ | BR | HJ | TM | I H | WC | PO | MF | MO | DP | ZT | KT | CV | MA | EC | PH | WN | TB | GD | TC | RR | HM | LW | LM | RP | RS |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | SNo. | Jolly | Name | Cod | h
AB01 | Substructure façade | B | 96.4286 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 1 | Yes |  |  | 0
AB01 | Frame installation | C | 100.3846 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2 | Yes |  |  | 0
AB01 | Glazing modules installation | D | 100.3846 | 2 | 5 | -5 | 5 | -5 | 5 | -5 | 5 | -5 | 5 | -5 | 5 | -5 | 5 | -5 | 5 | -5 | 5 | -5 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 45 | 2 | 40.3448 |  |  | 45 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 3 | Yes |  |  | 0
AB01 | Sealing & Insulation | E | 81.5625 | 2 | 5 | -5 | 5 | -5 | 5 | -5 | 5 | -5 | 5 | -5 | 5 | -5 | 5 | -5 | 5 | -5 | 5 | -5 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 45 | 2 | 49.6552 |  |  | 45 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 4 | Yes |  |  | 0
[127 empty] | 5 | Yes |  |  | 0
[127 empty] | 6 | Yes |  |  | 0
[127 empty] | 7 | Yes |  |  | 0
[127 empty] | 8 | Yes |  |  | 0
[127 empty] | 9 | Yes |  |  | 0
[127 empty] | 10 | Yes |  |  | 0
[127 empty] | 11 | Yes |  |  | 0
[127 empty] | 12 | Yes |  |  | 0
[127 empty] | 13 | Yes |  |  | 0
[127 empty] | 14 | Yes |  |  | 0
[127 empty] | 15 | Yes |  |  | 0
[127 empty] | 16 | Yes |  |  | 0
[127 empty] | 17 | Yes |  |  | 0
[127 empty] | 18 | Yes |  |  | 0
[127 empty] | 19 | Yes |  |  | 0
[127 empty] | 20 | Yes |  |  | 0
[127 empty] | 21 | Yes |  |  | 0
[127 empty] | 22 | Yes |  |  | 0
[127 empty] | 23 | Yes |  |  | 0
[127 empty] | 24 | Yes |  |  | 0
[127 empty] | 25 | Yes |  |  | 0
[127 empty] | 26 | Yes |  |  | 0
[127 empty] | 27 | Yes |  |  | 0
[127 empty] | 28 | Yes |  |  | 0
[127 empty] | 29 | Yes |  |  | 0
[127 empty] | 30 | Yes |  |  | 0
[127 empty] | 31 | Yes |  |  | 0
[127 empty] | 32 | Yes |  |  | 0
[127 empty] | 33 | Yes |  |  | 0
[127 empty] | 34 | Yes |  |  | 0
[127 empty] | 35 | Yes |  |  | 0
[127 empty] | 36 | Yes |  |  | 0
[127 empty] | 37 | Yes |  |  | 0
[127 empty] | 38 | Yes |  |  | 0
[127 empty] | 39 | Yes |  |  | 0
[127 empty] | 40 | Yes |  |  | 0
[127 empty] | 41 | Yes |  |  | 0

## Week3
[64 empty] | Codes | Description |  |  | Field | Value |  | Presence List
[64 empty] | Yes | Yes |  |  | h/D | 9 |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 41 | WR
[64 empty] | No | No |  |  | d | 5 |  | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd.
[64 empty] | J-ML | Management and logistics |  |  | h/W | 45 |  | AB | BP | CS | DG | HS | KR | MM | NM | LO | HD | DB | ME | RZ | FP | BA | SJ | BR | HJ | TM | I H | WC | PO | MF | MO | DP | ZT | KT | CV | MA | EC | PH | WN | TB | GD | TC | RR | HM | LW | LM | RP | RS
[64 empty] | J-S | Special work | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Scheduled
[64 empty] | J-A | Additional work |  |  |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 1845 | Total
[64 empty] | fd. | Full day
[64 empty] | hd. | Half day
Week3 Scheduling
[5 empty] | X1 - Level 0 | [17 empty] | X2 - Level 1 | [17 empty] | X3 - Level 2 | [10 empty] | Offer | [13 empty] | MA / Crew
|  |  | Performance |  | EAB |  | EBC |  | ECD |  | SA1B1 |  | SB1C1 |  | SC1D1 |  | WAB |  | WBC |  | WCD |  | EAB |  | EBC |  | ECD |  | SA1B1 |  | SB1C1 |  | SC1D1 |  | WAB |  | WBC |  | WCD |  | EAB |  | EBC |  | ECD |  | SA1B1 |  | SB1C1 |  | SC1D1 |  | WAB |  | WBC |  | WCD |  |  |  |  | Crew 1 | Crew 2 | 1 | 2 | 1 | 2 |  |  |  | AB | BP | CS | DG | HS | KR | MM | NM | LO | HD | DB | ME | RZ | FP | BA | SJ | BR | HJ | TM | I H | WC | PO | MF | MO | DP | ZT | KT | CV | MA | EC | PH | WN | TB | GD | TC | RR | HM | LW | LM | RP | RS |  |  | Working hours crew 1 | [5 empty] | Working hours crew 2
Process | Activity |  | QTY/W | WR | [54 empty] | TUS | WR | h |  |  | Fe | Fe | MA | MA |  |  |  | AB | BP | CS | DG | HS | KR | MM | NM | LO | HD | DB | ME | RZ | FP | BA | SJ | BR | HJ | TM | I H | WC | PO | MF | MO | DP | ZT | KT | CV | MA | EC | PH | WN | TB | GD | TC | RR | HM | LW | LM | RP | RS |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | SNo. | Jolly | Name | Cod | h
AB01 | Substructure façade | B | 96.4286 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 1 | Yes |  |  | 0
AB01 | Frame installation | C | 100.3846 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2 | Yes |  |  | 0
AB01 | Glazing modules installation | D | 100.3846 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 3 | Yes |  |  | 0
AB01 | Sealing & Insulation | E | 81.5625 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 4 | Yes |  |  | 0
[127 empty] | 5 | Yes |  |  | 0
[127 empty] | 6 | Yes |  |  | 0
[127 empty] | 7 | Yes |  |  | 0
[127 empty] | 8 | Yes |  |  | 0
[127 empty] | 9 | Yes |  |  | 0
[127 empty] | 10 | Yes |  |  | 0
[127 empty] | 11 | Yes |  |  | 0
[127 empty] | 12 | Yes |  |  | 0
[127 empty] | 13 | Yes |  |  | 0
[127 empty] | 14 | Yes |  |  | 0
[127 empty] | 15 | Yes |  |  | 0
[127 empty] | 16 | Yes |  |  | 0
[127 empty] | 17 | Yes |  |  | 0
[127 empty] | 18 | Yes |  |  | 0
[127 empty] | 19 | Yes |  |  | 0
[127 empty] | 20 | Yes |  |  | 0
[127 empty] | 21 | Yes |  |  | 0
[127 empty] | 22 | Yes |  |  | 0
[127 empty] | 23 | Yes |  |  | 0
[127 empty] | 24 | Yes |  |  | 0
[127 empty] | 25 | Yes |  |  | 0
[127 empty] | 26 | Yes |  |  | 0
[127 empty] | 27 | Yes |  |  | 0
[127 empty] | 28 | Yes |  |  | 0
[127 empty] | 29 | Yes |  |  | 0
[127 empty] | 30 | Yes |  |  | 0
[127 empty] | 31 | Yes |  |  | 0
[127 empty] | 32 | Yes |  |  | 0
[127 empty] | 33 | Yes |  |  | 0
[127 empty] | 34 | Yes |  |  | 0
[127 empty] | 35 | Yes |  |  | 0
[127 empty] | 36 | Yes |  |  | 0
[127 empty] | 37 | Yes |  |  | 0
[127 empty] | 38 | Yes |  |  | 0
[127 empty] | 39 | Yes |  |  | 0
[127 empty] | 40 | Yes |  |  | 0
[127 empty] | 41 | Yes |  |  | 0

## Week4
[64 empty] | Codes | Description |  |  | Field | Value |  | Presence List
[64 empty] | Yes | Yes |  |  | h/D | 9 |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 41 | WR
[64 empty] | No | No |  |  | d | 5 |  | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd. | fd.
[64 empty] | J-ML | Management and logistics |  |  | h/W | 45 |  | AB | BP | CS | DG | HS | KR | MM | NM | LO | HD | DB | ME | RZ | FP | BA | SJ | BR | HJ | TM | I H | WC | PO | MF | MO | DP | ZT | KT | CV | MA | EC | PH | WN | TB | GD | TC | RR | HM | LW | LM | RP | RS
[64 empty] | J-S | Special work | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Scheduled
[64 empty] | J-A | Additional work |  |  |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 1845 | Total
[64 empty] | fd. | Full day
[64 empty] | hd. | Half day
Week4 Scheduling
[5 empty] | X1 - Level 0 | [17 empty] | X2 - Level 1 | [17 empty] | X3 - Level 2 | [10 empty] | Offer | [13 empty] | MA / Crew
|  |  | Performance |  | EAB |  | EBC |  | ECD |  | SA1B1 |  | SB1C1 |  | SC1D1 |  | WAB |  | WBC |  | WCD |  | EAB |  | EBC |  | ECD |  | SA1B1 |  | SB1C1 |  | SC1D1 |  | WAB |  | WBC |  | WCD |  | EAB |  | EBC |  | ECD |  | SA1B1 |  | SB1C1 |  | SC1D1 |  | WAB |  | WBC |  | WCD |  |  |  |  | Crew 1 | Crew 2 | 1 | 2 | 1 | 2 |  |  |  | AB | BP | CS | DG | HS | KR | MM | NM | LO | HD | DB | ME | RZ | FP | BA | SJ | BR | HJ | TM | I H | WC | PO | MF | MO | DP | ZT | KT | CV | MA | EC | PH | WN | TB | GD | TC | RR | HM | LW | LM | RP | RS |  |  | Working hours crew 1 | [5 empty] | Working hours crew 2
Process | Activity |  | QTY/W | WR | [54 empty] | TUS | WR | h |  |  | Fe | Fe | MA | MA |  |  |  | AB | BP | CS | DG | HS | KR | MM | NM | LO | HD | DB | ME | RZ | FP | BA | SJ | BR | HJ | TM | I H | WC | PO | MF | MO | DP | ZT | KT | CV | MA | EC | PH | WN | TB | GD | TC | RR | HM | LW | LM | RP | RS |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | SNo. | Jolly | Name | Cod | h
AB01 | Substructure façade | B | 96.4286 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | -5 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 1 | Yes |  |  | 0
AB01 | Frame installation | C | 100.3846 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 2 | Yes |  |  | 0
AB01 | Glazing modules installation | D | 100.3846 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 3 | Yes |  |  | 0
AB01 | Sealing & Insulation | E | 81.5625 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | -12 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 4 | Yes |  |  | 0
[127 empty] | 5 | Yes |  |  | 0
[127 empty] | 6 | Yes |  |  | 0
[127 empty] | 7 | Yes |  |  | 0
[127 empty] | 8 | Yes |  |  | 0
[127 empty] | 9 | Yes |  |  | 0
[127 empty] | 10 | Yes |  |  | 0
[127 empty] | 11 | Yes |  |  | 0
[127 empty] | 12 | Yes |  |  | 0
[127 empty] | 13 | Yes |  |  | 0
[127 empty] | 14 | Yes |  |  | 0
[127 empty] | 15 | Yes |  |  | 0
[127 empty] | 16 | Yes |  |  | 0
[127 empty] | 17 | Yes |  |  | 0
[127 empty] | 18 | Yes |  |  | 0
[127 empty] | 19 | Yes |  |  | 0
[127 empty] | 20 | Yes |  |  | 0
[127 empty] | 21 | Yes |  |  | 0
[127 empty] | 22 | Yes |  |  | 0
[127 empty] | 23 | Yes |  |  | 0
[127 empty] | 24 | Yes |  |  | 0
[127 empty] | 25 | Yes |  |  | 0
[127 empty] | 26 | Yes |  |  | 0
[127 empty] | 27 | Yes |  |  | 0
[127 empty] | 28 | Yes |  |  | 0
[127 empty] | 29 | Yes |  |  | 0
[127 empty] | 30 | Yes |  |  | 0
[127 empty] | 31 | Yes |  |  | 0
[127 empty] | 32 | Yes |  |  | 0
[127 empty] | 33 | Yes |  |  | 0
[127 empty] | 34 | Yes |  |  | 0
[127 empty] | 35 | Yes |  |  | 0
[127 empty] | 36 | Yes |  |  | 0
[127 empty] | 37 | Yes |  |  | 0
[127 empty] | 38 | Yes |  |  | 0
[127 empty] | 39 | Yes |  |  | 0
[127 empty] | 40 | Yes |  |  | 0
[127 empty] | 41 | Yes |  |  | 0

## MonitoringWeek1
[35 empty] | Codes | Description |  |  | Field | Value
[35 empty] | Yes | Yes |  |  | h/D | 9
[35 empty] | No | No |  |  | d | 5
[35 empty] | J-ML | Management and logistics |  |  | h/W
[35 empty] | J-S | Special work
[35 empty] | J-A | Additional work
[35 empty] | fd. | Full day
[35 empty] | hd. | Half day
Monitoring Week1
[5 empty] | X1 - Level 0 | [8 empty] | X2 - Level 1 | [8 empty] | X3 - Level 2
|  |  | Performance |  | EAB | EBC | ECD | SA1B1 | SB1C1 | SC1D1 | WAB | WBC | WCD | EAB | EBC | ECD | SA1B1 | SB1C1 | SC1D1 | WAB | WBC | WCD | EAB | EBC | ECD | SA1B1 | SB1C1 | SC1D1 | WAB | WBC | WCD
Process | Activity |  | QTY/W | WR | [27 empty] | TUM | WR | h | Fe | Fe | MA | MA
AB01 | Substructure façade | B
AB01 | Frame installation | C
AB01 | Glazing modules installation | D
AB01 | Sealing & Insulation | E